## Sheet1
Ben Roberts - Programming Log | Task | Details | Estimated Time | Actual Time | Outcome | Outcome Details
| Unity Engine Basics | Learning the different project types, understanding the inspector window and heirarchy | 2 Hours | 4 Hours | Became significantly more confident with Unity and its UI interfaces | See Learning Journal
| Third-Person Player Movement | Wanting to understand simple movement and moving through a 3D space | 1.5 Hours | 2 Hours | Can understand basic movement with scripting and the use of components | N/A
| Unity Particle System | Want to create a wide range of different effects and particles | 2 Hours | 6 Hours | Particles are fun, lots more to dive deeper into | See Learning Journal
| Lighting | Testing on how to create an atmospheric scene | 1 Hour | 1.5 Hours | Leant how the difference between all the light sources (spot, area, directional) + URP & HDRP Project types | See Learning Journal
| Horror Game Research (Reading Week) | Research into mechanics that appear in Horror related games | 2.5 Hours | 2 Hours | Understood the 4 scripts I will need to create for my final submission | N/A
| Post Processing Effects | Looking into adding polish to a piece of work - (colour correction, motion blur, bloom etc) | 1 Hour | 2 Hours | Understood the variety of Post Processing effects to add multiple layers of polish to any form of game | See Learning Journal
| First Person Movement | Learning how to create first person movement, for the keyboard + mouse input | 2 Hours | 1.5 Hours | Fully functional first person controller | See Learning Journal
| Flashlight Toggle | Learning how to create the classic flashlight toggle mechanic | 1 Hour | 30 Minutes | Allowing the player to toggle on and off the flashflight with F | See Learning Journal
| Flickering Lights | Learning how to add an eeiry atmosphere with flicking light sources | 1 Hour | 1.5 Hours | At random intervals scripted light sources will flicker on and off repeatedly | See Learning Journal